{"text_format":"2","workbook":"xlsx","n_sheets":9,"sheets":["ios原生（胡志伟）","公司设置（胡志伟）","公告（董建强）","工作汇报（董建强）","流程（胡志伟）","考勤（熊伟）","日程提醒（熊伟）","任务（熊伟）","报销（熊伟）"],"not_rendered":{"charts":0,"images":30,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"ios原生（胡志伟）","index":0,"n_rows":16,"n_cols":7,"rows_kept":16,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["发现界面",1,"在发现的界面中，看到所在展示的应用程序中空白处显示灰色",null,"已处理","2017-07-29","2017-08-01"]
["系统消息助手/会话/新公告",2,"点击系统助手点击别人发的新公告进入后再按返回键后就会出现返回框上面一片白并且没有返回键",null,"已处理","2017-07-31","2017-08-01"]
["配置测试环境",8,"点击配置测试环境就会闪退",null,"已处理","2017-07-31","2017-08-01"]
["发现",3,"图标显示方框不显示正常图标",null,"已处理","2017-07-31","2017-08-01"]
["iOS原生",4,"更新后刚登入会出现闪退情况修改密码退出再登入后会话到登入左右一直多按几次会出现闪退情况，注册新用户后输入账号和密码再点击登入键登入或切换另外一个账号登入后大概过几秒钟就会出现闪退情况","版本号2.1.3(2017073103)",null,"2017-08-01"]
["登入界面",5,"手机账号登入填写错误在账号填写错误的情况下点击登入就会显示一直登入大概过了一分钟后会显示登入失败请检查网络。本应该提示密码或账号错误",null,null,"2017-08-01"]
["找回密码",6,"找回密码、输入好了要找回的的账号然后没有输入验证码就直接输入新修改的新密码点击确定后就会出现闪退的情况","版本号2.1.3(2017073103)",null,"2017-08-01"]
["我的/二维码和通讯录/",7,"别人扫描我的二维码添加好友请求后会话区域不会显示未读标签",null,null,"2017-08-01"]
["公告",8,"当发布公告的时候，需要添加地理位置信息，点击地理位置图标，进入地图界面，但是选择位置信息无法进行打钩","属于未完成内容",null,"2017-08-01"]
["会话/群主",9,"被群主移除了群还能看到群成员信息",null,null,"2017-08-01"]
[]
[]
[]
[]
[null,null,null,"                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                   "]

{"sheet":"公司设置（胡志伟）","index":1,"n_rows":3,"n_cols":7,"rows_kept":3,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["公司设置",1,"个人信息中的联系方式有下滑线但点击没反应","联系方式没有点击事件，处于不可修改的状态，所以点击是没有反应的","已处理","2017-07-31","2017-07-31"]
["公司设置/个人信息",5,"我的个人信息头像更改后不会显示更改后的头像",null,"已处理","2017-07-31","2017-07-31"]

{"sheet":"公告（董建强）","index":2,"n_rows":2,"n_cols":7,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["公告",1]

{"sheet":"工作汇报（董建强）","index":3,"n_rows":3,"n_cols":7,"rows_kept":3,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["工作汇报",1,"进入工作汇报界面，点击右上角“+”，编辑日报，当想要取消编写日报，点击“取消”按钮无效。",null,null,"2017-07-29"]
[null,2,"写日报界面，点击照相的图标，点击“拍照”完后，没有写显示照片；当点击“从相册中选择”，也无法调用起照片",null,"已处理","2017-07-29","2017-07-31"]

{"sheet":"流程（胡志伟）","index":4,"n_rows":4,"n_cols":7,"rows_kept":4,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["流程",1,"流程/管理/新建流程/选择流程模板/设置选项/添加字段，添加字段完成后不会立即显示，无法刷新，要退出去后在次进来才能显示添加完的字段",null,null,"2017-07-31"]
[null,2,"流程/申请，选择要申请的流程，进入页面后选择添加照片，然后完成会一直处于加载状态，重新退出去在我申请的流程下才会显示刚刚提交完成的流程，但都没有照片，再次申请提交选择相机照片无法调取。",null,null,"2017-07-31"]
[null,3,"流程中申请。申请流程提交到选项中选择不了审批的人也提交不了","在创建流程模板的时候，如果设置审批人是不可修改的，那么进入申请流程的时候，提交到这一栏的审批人是无法进行修改的。（流程模板“666”，提交到的审批人已被设置成不可修改）","已处理","2017-07-31","2017-07-31"]

{"sheet":"考勤（熊伟）","index":5,"n_rows":8,"n_cols":7,"rows_kept":8,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["考勤",1,"在考勤界面中，点击“签到”，发现签到的按钮是无效的，无法进行签到",null,null,"2017-07-29"]
[]
[]
[]
[]
[]
[{"$nulls":4},"`"]

{"sheet":"日程提醒（熊伟）","index":6,"n_rows":4,"n_cols":7,"rows_kept":4,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["日程提醒",1,"在日程提醒中，在点击我的日程中任意一个日程，点击右上角，有“编辑”和“删除”，但是显示的结果是有些挡住了删除",null,null,"2017-07-29"]
[null,2,"在日程提醒中，完成创建时间后，无论是选择限定到时提醒还是每天都提醒，提醒时间到了没有提醒提示，刷新重进创建的日程提醒，限定时间的会显示提醒已过期，没有限定时间的提醒会显示提醒结束，但都没有收到提醒提示",null,"   ","2017-08-01"]
[null,3,"新建日程中，重复如果选择每天重复次数4次以上就无法提交，出于一直加载的状态，退出后重进提交失败，没有显示",null,null,"2017-08-01"]

{"sheet":"任务（熊伟）","index":7,"n_rows":4,"n_cols":7,"rows_kept":4,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["任务",1,"任务/发布任务，新建发布任务，这边发布完任务后，接受任务的那边只能收到信息，但无法显示任务信息，任务列表也没有显示，评论也无法显示，任务发布图片时一直处于加载状态，退出去重新进入可以看到发布的任务，但没有图片。",null,null,"2017-07-31"]
[null,2,"任务/发布任务，任务发布后，接受任务的人在任务应用中的收到的任务一栏无显示，刷新重进也没有",null,null,"2017-08-01"]
[null,3,"任务发布完成后，接受任务的人只有提示，点进去的任务详情空白什么的看不到，评论会弹Alert窗口，任务列表也无法显示接收到的任务",null,null,"2017-08-01"]

{"sheet":"报销（熊伟）","index":8,"n_rows":2,"n_cols":7,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
["功能模块","序号","问题","备注","处理情况","提交时间","完成时间"]
["报销",1,"报销/添加消费记录，添加完成后选择完审批出资人后，选择需要报销的消费，然后提交上去后，等审批人还没审批完成之前撤销报销单，审批人和出资人那不会提示对方已撤销报销单，点击进去会一直卡在加载页面，无法显示。",null,null,"207/7/31"]